## Sheet1
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
S1 | S1 | US-001 | Environment Setup & Repository Initialization | MUST HAVE | VS Code, Git | Tharun Kumar C | ✅ Completed
S1 | S1 | US-002 | Backend Setup using FastAPI and Uvicorn | MUST HAVE | Python 3.8+, Pip | Tharun Kumar C | ✅ Completed
S2 | S2 | US-003 | Integration of APIs (GNews, SerpAPI, Reddit, Twitter) | MUST HAVE | API Keys | Tharun Kumar C | ✅ Completed
S2 | S2 | US-004 | OpenAI GPT & LLaMA Integration for NLP | SHOULD HAVE | OpenAI API Key | Tharun Kumar C | ✅ Completed
S3 | S3 | US-005 | Data Collection Pipeline Initialization | MUST HAVE | Pandas, Requests | Tharun Kumar C | ✅ Completed
S3 | S3 | US-006 | Data Cleaning & Sentiment Computation | MUST HAVE | TextBlob, NumPy | Tharun Kumar C | ✅ Completed
S4 | S4 | US-007 | Trend Forecasting Model Development | SHOULD HAVE | Prophet, scikit-learn | Tharun Kumar C | ✅ Completed
S4 | S4 | US-008 | Alert System Configuration (spikes, sentiment, trends) | MUST HAVE | Slack Webhook | Tharun Kumar C | ✅ Completed
S5 | S5 | US-009 | Frontend Development (React + Tailwind) | MUST HAVE | Node.js, npm | Tharun Kumar C | ✅ Completed
S5 | S5 | US-010 | Dashboard UI Design & Chart Visualization | MUST HAVE | Recharts, Lucide Icons | Tharun Kumar C | ✅ Completed
S6 | S6 | US-011 | Competitor & Domain Selector Modal | COULD HAVE | React Modal, Context API | Tharun Kumar C | ✅ Completed
S6 | S6 | US-012 | Customizable Filters (Time Range, Sentiment, Source) | SHOULD HAVE | React State Management | Tharun Kumar C | ✅ Completed
S7 | S7 | US-013 | API–Frontend Integration | MUST HAVE | CORS Middleware | Tharun Kumar C | ✅ Completed
S7 | S7 | US-014 | Alert Visualization and Notification Center | SHOULD HAVE | Slack API | Tharun Kumar C | ✅ Completed
S8 | S8 | US-015 | Testing of Data APIs and Alert Logic | MUST HAVE | Postman, cURL | Tharun Kumar C | ✅ Completed
S8 | S8 | US-016 | Dashboard Deployment (Render / Vercel) | MUST HAVE | Render, GitHub CI/CD | Tharun Kumar C | ✅ Completed
S9 | S9 | US-017 | Theme Toggle Implementation (Dark/Light Mode) | COULD HAVE | Tailwind Theme | Tharun Kumar C | ✅ Completed
S9 | S9 | US-018 | News Feed Page with Filtering Options | MUST HAVE | News API Data | Tharun Kumar C | ✅ Completed
S10 | S10 | US-019 | Social Media Sentiment Analytics Page | MUST HAVE | Reddit & Twitter API | Tharun Kumar C | ✅ Completed
S10 | S10 | US-020 | Competitor Insights Panel with Metrics | SHOULD HAVE | Chart Components | Tharun Kumar C | ✅ Completed
S11 | S11 | US-021 | Export Feature for Reports and Data Charts | COULD HAVE | CSV Export Package | Tharun Kumar C | ✅ Completed
S11 | S11 | US-022 | Data Validation and Error Handling System | MUST HAVE | Exception Logging | Tharun Kumar C | ✅ Completed
S12 | S12 | US-023 | Real-time Alert Push via Slack Webhook | SHOULD HAVE | Slack API | Tharun Kumar C | ✅ Completed
S12 | S12 | US-024 | Automated Data Refresh & Caching Mechanism | COULD HAVE | LocalStorage, Cache | Tharun Kumar C | ✅ Completed
S13 | S13 | US-025 | Final Report & Presentation Preparation | MUST HAVE | PowerPoint, Canva | Tharun Kumar C | ✅ Completed
S13 | S13 | US-026 | User Onboarding Documentation | SHOULD HAVE | Readme, Docsify | Tharun Kumar C | ✅ Completed
S14 | S14 | US-027 | Competitor Benchmark Comparison Table | COULD HAVE | Table Library | Tharun Kumar C | ✅ Completed
S14 | S14 | US-028 | Interactive Trend Timelines | SHOULD HAVE | Plotly, Matplotlib | Tharun Kumar C | ✅ Completed
S15 | S15 | US-029 | Multi-sector Intelligence Summary View | MUST HAVE | Filter Modules | Tharun Kumar C | ✅ Completed
S15 | S15 | US-030 | Insight Export to PDF | COULD HAVE | ReportLab | Tharun Kumar C | ✅ Completed