## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
S1 | S1 | US-001 | Environment Setup & Repository Initialization | MUST HAVE | VS Code, Git | Tharun Kumar C | ✅ Completed
S1 | S1 | US-002 | Backend Setup using FastAPI and Uvicorn | MUST HAVE | Python 3.8+, Pip | Tharun Kumar C | ✅ Completed
S2 | S2 | US-003 | Integration of APIs (GNews, SerpAPI, Reddit, Twitter) | MUST HAVE | API Keys | Tharun Kumar C | ✅ Completed
S2 | S2 | US-004 | OpenAI GPT & LLaMA Integration for NLP | SHOULD HAVE | OpenAI API Key | Tharun Kumar C | ✅ Completed
S3 | S3 | US-005 | Data Collection Pipeline Initialization | MUST HAVE | Pandas, Requests | Tharun Kumar C | ✅ Completed
S3 | S3 | US-006 | Data Cleaning & Sentiment Computation | MUST HAVE | TextBlob, NumPy | Tharun Kumar C | ✅ Completed
S4 | S4 | US-007 | Trend Forecasting Model Development | SHOULD HAVE | Prophet, scikit-learn | Tharun Kumar C | ✅ Completed
S4 | S4 | US-008 | Alert System Configuration (spikes, sentiment, trends) | MUST HAVE | Slack Webhook | Tharun Kumar C | ✅ Completed
S5 | S5 | US-009 | Frontend Development (React + Tailwind) | MUST HAVE | Node.js, npm | Tharun Kumar C | ✅ Completed
S5 | S5 | US-010 | Dashboard UI Design & Chart Visualization | MUST HAVE | Recharts, Lucide Icons | Tharun Kumar C | ✅ Completed
S6 | S6 | US-011 | Competitor & Domain Selector Modal | COULD HAVE | React Modal, Context API | Tharun Kumar C | ✅ Completed
S6 | S6 | US-012 | Customizable Filters (Time Range, Sentiment, Source) | SHOULD HAVE | React State Management | Tharun Kumar C | ✅ Completed
S7 | S7 | US-013 | API–Frontend Integration | MUST HAVE | CORS Middleware | Tharun Kumar C | ✅ Completed
S7 | S7 | US-014 | Alert Visualization and Notification Center | SHOULD HAVE | Slack API | Tharun Kumar C | ✅ Completed
S8 | S8 | US-015 | Testing of Data APIs and Alert Logic | MUST HAVE | Postman, cURL | Tharun Kumar C | ✅ Completed
S8 | S8 | US-016 | Dashboard Deployment (Render / Vercel) | MUST HAVE | Render, GitHub CI/CD | Tharun Kumar C | ✅ Completed
S9 | S9 | US-017 | Theme Toggle Implementation (Dark/Light Mode) | COULD HAVE | Tailwind Theme | Tharun Kumar C | ✅ Completed
S9 | S9 | US-018 | News Feed Page with Filtering Options | MUST HAVE | News API Data | Tharun Kumar C | ✅ Completed
S10 | S10 | US-019 | Social Media Sentiment Analytics Page | MUST HAVE | Reddit & Twitter API | Tharun Kumar C | ✅ Completed
S10 | S10 | US-020 | Competitor Insights Panel with Metrics | SHOULD HAVE | Chart Components | Tharun Kumar C | ✅ Completed
S11 | S11 | US-021 | Export Feature for Reports and Data Charts | COULD HAVE | CSV Export Package | Tharun Kumar C | ✅ Completed
S11 | S11 | US-022 | Data Validation and Error Handling System | MUST HAVE | Exception Logging | Tharun Kumar C | ✅ Completed
S12 | S12 | US-023 | Real-time Alert Push via Slack Webhook | SHOULD HAVE | Slack API | Tharun Kumar C | ✅ Completed
S12 | S12 | US-024 | Automated Data Refresh & Caching Mechanism | COULD HAVE | LocalStorage, Cache | Tharun Kumar C | ✅ Completed
S13 | S13 | US-025 | Final Report & Presentation Preparation | MUST HAVE | PowerPoint, Canva | Tharun Kumar C | ✅ Completed
S13 | S13 | US-026 | User Onboarding Documentation | SHOULD HAVE | Readme, Docsify | Tharun Kumar C | ✅ Completed
S14 | S14 | US-027 | Competitor Benchmark Comparison Table | COULD HAVE | Table Library | Tharun Kumar C | ✅ Completed
S14 | S14 | US-028 | Interactive Trend Timelines | SHOULD HAVE | Plotly, Matplotlib | Tharun Kumar C | ✅ Completed
S15 | S15 | US-029 | Multi-sector Intelligence Summary View | MUST HAVE | Filter Modules | Tharun Kumar C | ✅ Completed
S15 | S15 | US-030 | Insight Export to PDF | COULD HAVE | ReportLab | Tharun Kumar C | ✅ Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-001 | 1 | Project Repository & Environment Setup | 2025-08-25 | 2025-08-27 | Tharun Kumar C | Setup | 3 - Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | FastAPI and Uvicorn Configuration | 2025-08-28 | 2025-08-30 | Tharun Kumar C | Backend Setup | 3 - Completed | 6 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 3 | API Integration (GNews, SerpAPI, Reddit, Twitter) | 2025-08-31 | 2025-09-03 | Tharun Kumar C | Integration | 3 - Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 4 | Data Cleaning & Sentiment Pipeline (TextBlob) | 2025-09-04 | 2025-09-06 | Tharun Kumar C | Data Processing | 3 - Completed | 10 | 3 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 5 | NLP Integration using OpenAI GPT | 2025-09-07 | 2025-09-10 | Tharun Kumar C | NLP Setup | 3 - Completed | 9 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 6 | Prophet Forecasting Model Development | 2025-09-11 | 2025-09-13 | Tharun Kumar C | AI Forecasting | 3 - Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 7 | Slack Alert System Configuration | 2025-09-14 | 2025-09-16 | Tharun Kumar C | Alerts | 3 - Completed | 6 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 8 | React Frontend Setup with Tailwind | 2025-09-17 | 2025-09-19 | Tharun Kumar C | Frontend | 3 - Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | 9 | Chart Components with Recharts | 2025-09-20 | 2025-09-22 | Tharun Kumar C | Visualization | 3 - Completed | 5 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | 10 | Dashboard & Domain Selector Modal | 2025-09-23 | 2025-09-26 | Tharun Kumar C | UI Enhancement | 3 - Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | 11 | API–Frontend Integration | 2025-09-27 | 2025-09-29 | Tharun Kumar C | Integration | 3 - Completed | 7 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | 12 | Alert Visualization & Notification Center | 2025-09-30 | 2025-10-02 | Tharun Kumar C | Alerts | 3 - Completed | 9 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | 13 | Testing of Data APIs & Forecast Logic | 2025-10-03 | 2025-10-05 | Tharun Kumar C | Testing | 3 - Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | 14 | Dashboard Deployment (Render / Vercel) | 2025-10-06 | 2025-10-08 | Tharun Kumar C | Deployment | 3 - Completed | 6 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | 15 | Final Report & Presentation | 2025-10-09 | 2025-10-11 | Tharun Kumar C | Documentation | 3 - Completed | 5 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Standup Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | FastAPI server failed to start due to port conflicts | Updated server configuration and applied new CORS rules
Sprint 1 | Day 4 | API rate limits exceeded while testing SerpAPI | Implemented caching and retry delay mechanism
Sprint 2 | Day 6 | CSV header mismatch between GNews and Reddit data | Standardized schema using Pandas and column renaming
Sprint 2 | Day 8 | TextBlob misclassifying neutral posts as positive | Added regex-based text preprocessing and stopword filtering
Sprint 3 | Day 10 | Prophet model taking too long to train on large datasets | Reduced data window to 30-day rolling and increased step size
Sprint 3 | Day 12 | Slack webhook returned 403 error during alert tests | Regenerated Slack webhook and reauthorized workspace
Sprint 4 | Day 14 | Charts not rendering when CSV data empty | Added default placeholder dataset to prevent graph errors
Sprint 4 | Day 16 | Alert system triggered too many low-severity events | Refined thresholds and applied weighted averaging
Sprint 5 | Day 18 | Dashboard slow on first render | Implemented React Suspense and lazy loading for heavy components
Sprint 5 | Day 20 | Deployment build failed on Render platform | Fixed Python buildpack version and adjusted environment variables
Sprint 6 | Day 22 | Alert timestamps not matching server timezone | Configured timezone handling in FastAPI and Slack
Sprint 6 | Day 23 | CSV files overwriting old data unintentionally | Added timestamped filenames for each data refresh
Sprint 7 | Day 25 | Prophet prediction output missing confidence intervals | Enabled uncertainty intervals in model settings
Sprint 7 | Day 27 | API response delay when multiple requests triggered | Cached results using FastAPI background tasks
Sprint 8 | Day 29 | Final report taking long to export | Optimized chart export using async calls

## Retrospection
Sprint No | Sprint Start Date | Sprint End Date | Team Member Name | Start Doing | Stop Doing | Continue Doing | Action Taken
Sprint 1 | 2025-08-25 | 2025-08-30 | Tharun Kumar C | Maintaining environment setup logs | Skipping dependency checks | Properly documenting environment configurations | Created setup script and shared via README
Sprint 2 | 2025-08-31 | 2025-09-06 | Tharun Kumar C | Verifying API responses before integration | Trusting unvalidated CSV inputs | Keeping schema consistency across APIs | Added API response validator using Pandas
Sprint 3 | 2025-09-07 | 2025-09-13 | Tharun Kumar C | Automating sentiment computation | Manually cleaning data | Running preprocessing scripts daily | Integrated automated cleaning pipeline
Sprint 4 | 2025-09-14 | 2025-09-20 | Tharun Kumar C | Monitoring Prophet performance logs | Training model without tuning | Analyzing forecast metrics weekly | Improved accuracy by 8%
Sprint 5 | 2025-09-21 | 2025-09-26 | Tharun Kumar C | Modularizing React components | Hardcoding data in charts | Using reusable chart components | Reduced UI errors and increased scalability
Sprint 6 | 2025-09-27 | 2025-10-02 | Tharun Kumar C | Automating alert tests | Triggering manual tests | Testing alert thresholds automatically | Optimized alert detection logic
Sprint 7 | 2025-10-03 | 2025-10-08 | Tharun Kumar C | Performing load testing before deployment | Deploying without runtime checks | Testing APIs under high load | Improved API response speed by 25%
Sprint 8 | 2025-10-09 | 2025-10-11 | Tharun Kumar C | Preparing concise presentation slides | Adding too much technical detail | Maintaining clarity and structure in documentation | Delivered clear and investor-ready presentation